## Bug Metric
Iteration | Bug Metrics Score | Mitigation Plan executed
2 | 5 | Bugs were fixed during planned debugging time | NOTE: Iteration 1 in Pplog was invalid. Therefore, iterations reflected in this bug metric will start from Iteration 2.
3 | 16 | Stop current development and resolved the bugs immediately. No need for rescheduling done because bugs were fixed during planned debugging time
4 | 30 | No need for rescheduling done because bug were fixed during planned debugging time except for the bug #3 in BidPlacementServlet.java. Ming Yi will be debugging it in her next pp session.
5 | 55 | No need for rescheduling done because bug were fixed during planned debugging time.
6 | 134 | Extra debugging sessions were created to debug after Regression Testing #2 as bug metric is too high.
7 | 134 | Extra debugging sessions were created to debug after UAT as bug metric is too high and we were unable to finish fixing all the bugs within the first 3 debugging sessions. Subsequent task was cut short to allow more time for debugging.

## Iteration 2
Iteration 2 (12/9 - 18/9) |  | PM: Marc |  | (This corresponds to our actual Iteration 1)
S/N | Bug Description | Affected File | Date Identified | Time Identified | Identifier | Date Resolved | Time Resolved | Resolver | Bug Status | Impact | Bug Lifetime(Days) | Points | Severity | Points | Description
1 | Users will be able to access the webpage through URL without going through proper login procedures | login.jsp | 2016-09-15 | 16:31 | Ming Yi & Nilofar | 2016-09-18 | 21:17 | Ming Yi & Nilofar | Resolved | High impact | 3 | 5 | Critical Impact | 10 | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
[11 empty] | Total: | 5 | High impact | 5 | The system runs. However, some non-critical functionalities are not working.
[13 empty] | Low impact | 1 | Unimportant. Typo error or small user interface alignment issues.
Bug Status
Resolved
Unresolved
Formulas:
Bug Lifetime(Days) = IF([Date Identified]="","",IF([Date Resolved]="",TODAY()-[Date Identified],[Date Resolved]-[Date Identified]))

## Iteration 3
Iteration 3 (19/9 - 24/9) |  | PM: Jackson | (This corresponds to our actual Iteration 2)
S/N | Bug Description | Affected File | Date Identified | Time Identified | Identifier | Date Resolved | Time Resolved | Resolver | Bug Status | Impact | Bug Lifetime(Days) | Points | Severity | Points | Description
1 | Bids were added even though they were not validated | BidPlacementServlet.java | 2016-09-23 | 16:00 | Nilofar | 2016-09-23 | 16:17 | Yu Jian | Resolved | High impact | 0 | 5 | Critical Impact | 10 | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
2 | Buttons on Admin Sidebar are not highlighted when clicked onto a specific page | AdminSiderbar.jsp | 2016-09-23 | 16:30 | Yu Jian | 2016-09-23 | 16:34 | Yu Jian | Resolved | Low impact | 0 | 1 | High impact | 5 | The system runs. However, some non-critical functionalities are not working.
3 | Bootstrap Validator - parameters in the wrong order | BootstrapValidator.java | 2016-09-24 | 18:20 | Ming Yi & Marc | 2016-09-24 | 18:45 | Marc | Resolved | High impact | 0 | 5 | Low impact | 1 | Unimportant. Typo error or small user interface alignment issues.
4 | Course List is null when tried to display in bidSection.jsp even though connection to database already established | BidPlacementServlet.java | 2016-09-24 | 23:30 | Ming Yi | 2016-09-26 | 19:32 | Ming Yi | Resolved | High impact | 2 | 5
[11 empty] | Total: | 16 | Bug Status
Resolved
Unresolved
Formulas:
Bug Lifetime(Days) = IF([Date Identified]="","",IF([Date Resolved]="",TODAY()-[Date Identified],[Date Resolved]-[Date Identified]))

## Iteration 4
Iteration 4 (26/9 - 2/10) |  | PM: Nilofar | (This corresponds to our actual Iteration 3)
S/N | Bug Description | Affected File | Date Identified | Time Identified | Identifier | Date Resolved | Time Resolved | Resolver | Bug Status | Impact | Bug Lifetime(Days) | Points | Severity | Points | Description
1 | IllegalStateException - cannot call sendRedirect() after response has been commented | LoginAuthenticationServlet.java | 2016-09-28 | 10:03 | Ming Yi & Jackson | 2016-09-28 | 10:05 | Jackson | Resolved | Critical Impact | 0 | 10 | Critical Impact | 10 | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
2 | Students will be able to access the admin dashboard through URL after logging in | AdminHome.jsp | 2016-09-28 | 14:22 | Ming Yi | 2016-09-28 | 14:40 | Ming Yi & Jackson | Resolved | High impact | 0 | 5 | High impact | 5 | The system runs. However, some non-critical functionalities are not working.
3 | Students' eDollars were not deducted even after bidding was successful | BidPlacementServlet.java | 2016-09-28 | 14:55 | Ming Yi | 2016-09-28 | 15:12 | Ming Yi & Jackson | Resolved | High impact | 0 | 5 | Low impact | 1 | Unimportant. Typo error or small user interface alignment issues.
4 | Bid was not deleted from database | ConnectionManager.java | 2016-09-30 | 16:14 | Yu Jian and Marc | 2016-09-30 | 16:30 | Marc | Resolved | High impact | 0 | 5
5 | Bid table was not uploaded | BootstrapValidator.java | 2016-09-30 | 20:00 | Yu Jian and Marc | 2016-09-30 | 20:15 | Yu Jian | Resolved | High impact | 0 | 5 | Bug Status
[11 empty] | Total: | 30 | Resolved
Unresolved
Formulas:
Bug Lifetime(Days) = IF([Date Identified]="","",IF([Date Resolved]="",TODAY()-[Date Identified],[Date Resolved]-[Date Identified]))

## Iteration 5
Iteration 5 (3/10 - 15/10) |  | PM: Marc | (This corresponds to our actual Iteration 4)
S/N | Bug Description | Affected File | Date Identified | Time Identified | Identifier | Date Resolved | Time Resolved | Resolver | Bug Status | Impact | Bug Lifetime(Days) | Points | Severity | Points | Description
1 | Econs001 - No successful bids | AdminClearRound1Servrlet.java | 2016-10-07 | 18:45 | Nilofar and Jackson | 2016-10-08 | 15:00 | Yu Jian & Ming Yi | Resolved | High impact | 1 | 5 | Critical Impact | 10 | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
2 | Display shows that there are no bids for course-section But also displays the successful bids of other course-sections | AdminClearRound1Servrlet.java | 2016-10-07 | 20:15 | Nilofar and Jackson | 2016-10-08 | 15:00 | Yu Jian & Ming Yi | Resolved | High impact | 1 | 5 | High impact | 5 | The system runs. However, some non-critical functionalities are not working.
3 | Bids are successful even if the bid amount is less than the minimum bid amount of $10 | BidPlacement.java | 2016-10-08 | 13:45 | Jackson | 2016-10-08 | 13:55 | Nilofar | Resolved | High impact | 0 | 5 | Low impact | 1 | Unimportant. Typo error or small user interface alignment issues.
4 | Couldn't track the status of all the bids properly due to us not storing the status of bids inside the sql DB itself | ConnectionManager.java | 2016-10-08 | 16:21 | Ming Yi | 2016-10-08 | 17:00 | Ming Yi | Resolved | High impact | 0 | 5
5 | Bids were not deducted when they are failed | ClearingLogicServlet.java | 2016-10-08 | 18:30 | Ming Yi | 2016-10-08 | 19:00 | Yu Jian | Resolved | High impact | 0 | 5 | Bug Status
6 | Bootstrapping of data didn't start round automatically | AdminBootstrapServlet.java | 2016-10-11 | 12:00 | Ming Yi | 2016-10-11 | 12:14 | Ming Yi | Resolved | High impact | 0 | 5 | Resolved
7 | Deleting of bids didn’t work after we changed the context path of the application | StudentDropBidServlet.java | 2016-10-11 | 18:30 | Yu Jian | 2016-10-11 | 19:00 | Yu Jian | Resolved | High impact | 0 | 5 | Unresolved
8 | Bootstrapping didn't work anymore after requirement change, the uploading of the new data.zip caused system to not work | BootstrapCSVreader.java | 2016-10-12 | 14:30 | Ming Yi | 2016-10-12 | 15:10 | Yu Jian | Resolved | Critical Impact | 0 | 10
9 | Bids cannot be added when prerequisite is fulfilled | BidPlacementServlet.java | 2016-10-12 | 15:13 | Ming Yi | 2016-10-12 | 15:30 | Ming Yi | Resolved | High impact | 0 | 5
10 | after clicking on drop bid, was brought to bidSection.jsp | BidPlacementServlet.java | 2016-10-12 | 15:45 | Ming Yi | 2016-10-12 | 15:55 | Ming Yi | Resolved | High impact | 0 | 5
[11 empty] | Total: | 55
Formulas:
Bug Lifetime(Days) = IF([Date Identified]="","",IF([Date Resolved]="",TODAY()-[Date Identified],[Date Resolved]-[Date Identified]))

## Iteration 6
Iteration 6 (16/10 - 5/11) |  | PM: Ming Yi | (This corresponds to our actual Iteration 5)
S/N | Bug Description | Affected File | Date Identified | Time Identified | Identifier | Date Resolved | Time Resolved | Resolver | Bug Status | Impact | Bug Lifetime(Days) | Points | Severity | Points | Description
1 | Errors for bid.csv were not shown even when there should are errors in the data | BootstrapValidator.java | 2016-10-16 | 20:24 | Yu Jian | 2016-10-17 | 11:23 | Yu Jian | Resolved | High impact | 1 | 5 | Critical Impact | 10 | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
2 | Errors for courseCompleted.csv were shown even when there shouldn't be any errors | BootstrapValidator.java | 2016-10-16 | 20:24 | Yu Jian | 2016-10-17 | 11:50 | Yu Jian | Resolved | High impact | 1 | 5 | High impact | 5 | The system runs. However, some non-critical functionalities are not working.
3 | Validation errors remains even when page is refreshed | BidSection.jsp | 2016-10-19 | 18:35 | Ming Yi | 2016-10-26 | 16:23 | Nilofar | Resolved | Low impact | 7 | 1 | Low impact | 1 | Unimportant. Typo error or small user interface alignment issues.
4 | By right amy.ng.2009 can bid for IS101, but was given incomplete prereq error | BidPlacement.java | 2016-10-19 | 18:45 | Ming Yi | 2016-10-26 | 16:30 | Nilofar | Resolved | High impact | 7 | 5
5 | Gary.ng completed IS100, but bid.csv does not reflect as such. ParseCourseCompletion logic has problems. | BootstrapValidator.java | 2016-10-19 | 19:25 | Ming Yi | 2016-10-26 | 17:00 | Nilofar | Resolved | High impact | 7 | 5 | Bug Status
6 | Dawn.ng's successful bids also appear in drop bid page | dropBid.jsp | 2016-10-23 | 18:05 | Nilofar | 2016-10-23 | 18:30 | Marc | Resolved | Low impact | 0 | 1 | Resolved
7 | Amy.ng.2009 is not able to place a bid for a course offered by a school that is not hers in Round 2 | GetLiveBiddingTableServlet.jsva | 2016-10-23 | 18:47 | Marc | 2016-10-23 | 19:13 | Marc | Resolved | High impact | 0 | 5 | Unresolved
8 | Repeated display of successful bids of a student | DropSection.jsp | 2016-10-23 | 19:02 | Marc | 2016-10-23 | 19:23 | Marc | Resolved | Low impact | 0 | 1
9 | When bid is placed in Round 2, the bid is only shown in drop bid but not reflected real time | GetLiveBiddingTableServlet.jsva | 2016-10-23 | 21:30 | Marc | 2016-10-26 | 17:24 | Yu Jian | Resolved | Low impact | 3 | 1
10 | When requested a valid username for Drop Section web service, invalid username error is returned | DropSectionService.java | 2016-10-25 | 8:30 | Nilofar | 2016-10-25 | 9:30 | Marc | Resolved | High impact | 0 | 5
11 | When an input parameter is missing, the browser throws a null pointer exception | DropSectionService.java | 2016-10-25 | 8:37 | Nilofar | 2016-10-25 | 10:03 | Marc | Resolved | High impact | 0 | 5
12 | Error message is not displayed | DropSectionService.java | 2016-10-25 | 8:42 | Marc | 2016-10-25 | 10:26 | Marc | Resolved | High impact | 0 | 5
13 | Success message displayed but section was not dropped | DropSectionService.java | 2016-10-25 | 8:45 | Marc | 2016-10-25 | 11:15 | Marc | Resolved | High impact | 0 | 5
14 | When an input parameter is missing, the browser throws a null pointer exception | DumpUserService.java | 2016-10-25 | 8:47 | Marc | 2016-10-25 | 11:54 | Nilofar | Resolved | High impact | 0 | 5
15 | Error message not displayed in correct order | DumpUserService.java | 2016-10-25 | 8:55 | Marc | 2016-10-25 | 12:15 | Nilofar | Resolved | High impact | 0 | 5
16 | Error message not displayed in correct order | DumpBidService.java | 2016-10-25 | 9:00 | Nilofar | 2016-10-25 | 12:38 | Nilofar | Resolved | High impact | 0 | 5
17 | "Duplicate userid" was not shown when there was duplicate user ids in student.csv | BootstrapValidator.java | 2016-10-27 | 9:45 | Nilofar | 2016-10-27 | 16:32 | Marc | Resolved | High impact | 0 | 5
18 | "Invalid exam end" was no shown when exam end time is earlier than exam start time | BootstrapValidator.java | 2016-10-27 | 10:04 | Nilofar | 2016-10-27 | 17:10 | Marc | Resolved | High impact | 0 | 5
19 | Blank row of pre-requisite.csv was given error message of "blank course" when "blank course, blank prerequisite" should be returned | BootstrapValidator.java | 2016-10-27 | 10:23 | Nilofar | 2016-10-27 | 17:33 | Marc | Resolved | High impact | 0 | 5
20 | Blank row of course-completed.csv was given error message of "blank userid" when "blank userid, blank code" should be returned | BootstrapValidator.java | 2016-10-27 | 10:28 | Nilofar | 2016-10-27 | 17:58 | Marc | Resolved | High impact | 0 | 5
21 | Prerequisite has yet to be attempted but the course could be added into database | BootstrapValidator.java | 2016-10-27 | 10:32 | Nilofar | 2016-10-27 | 18:16 | Yu Jian | Resolved | High impact | 0 | 5
22 | Blank row of bid.csv was given error message of "blank userid" when "blank userid, blank amount, blank code, blank section " should be returned | BootstrapValidator.java | 2016-10-27 | 10:34 | Nilofar | 2016-10-28 | 22:44 | Nilofar | Resolved | High impact | 1 | 5
23 | "class and exam timetable clash" error was not returned when it should | BootstrapValidator.java | 2016-10-27 | 10:46 | Nilofar | 2016-10-28 | 23:40 | Nilofar | Resolved | High impact | 1 | 5
24 | Bids were not updated even when the course is similar. "exam timetable clash" error message was given instead | BootstrapValidator.java | 2016-10-27 | 10:46 | Nilofar | 2016-10-29 | 0:47 | Ming Yi | Resolved | High impact | 2 | 5
25 | NumberFormatException was given when invalid amounts were inserted | BidPlacementServlet.java | 2016-10-27 | 11:11 | Nilofar | 2016-10-31 | 12:47 | Jackson | Resolved | High impact | 4 | 5
26 | "class timetable clash" was not returned when it should | BidPlacementServlet.java | 2016-10-27 | 11:30 | Nilofar | 2016-10-31 | 13:50 | Jackson | Resolved | High impact | 4 | 5
27 | Calvin Ng's IS100 bid failed in round 1 when he should pass | Clearing round 1 - BiddingRoundServlet.java | 2016-10-27 | 12:15 | Nilofar | 2016-10-31 | 14:23 | Ming YI & Jackson | Resolved | High impact | 4 | 5
28 | Multiple bids at clearing price is successful when they shouldn’t be | Clearing round 1 - BiddingRoundServlet.java | 2016-10-27 | 12:44 | Nilofar | 2016-10-31 | 21:34 | Ming Yi | Resolved | High impact | 4 | 5
29 | e$ is not being refunded to the Student if the bid fails when the round is cleared | Clearing round 2 - BiddingRoundServlet.java | 2016-10-27 | 13:10 | Nilofar | 2016-10-31 | 21:45 | Ming Yi | Resolved | High impact | 4 | 5
30 | Students will be able to bid at min bid value and be successful even when the class is unable to accommodate all bids at min bid value | Clearing round 2 - GetLiveBiddingServlet.java | 2016-10-27 | 13:34 | Nilofar | 2016-10-31 | 23:28 | Ming Yi | Resolved | High impact | 4 | 5
[11 empty] | Total: | 134
Formulas:
Bug Lifetime(Days) = IF([Date Identified]="","",IF([Date Resolved]="",TODAY()-[Date Identified],[Date Resolved]-[Date Identified]))

## Iteration 7
Iteration 7 (6/11 - 17/11) |  | PM: Yu Jian | (This corresponds to our actual Iteration 6)
S/N | Bug Description | Affected File | Date Identified | Time Identified | Identifier | Date Resolved | Time Resolved | Resolver | Bug Status | Impact | Bug Lifetime(Days) | Points | Severity | Points | Description
1 | Users find it hard to find bid status after bidding | UI - StudentHomepage.jsp | 2016-11-03 | 16:00 | Iris & Rachel | 2016-11-07 | 12:13 | Ming Yi | Resolved | Low impact | 4 | 1 | Critical Impact | 10 | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
2 | Users find it hard to check total seats available and min bid value after live bidding | UI - bidSection.jsp | 2016-11-03 | 16:00 | Iris & Rachel | 2016-11-07 | 14:23 | Ming Yi | Resolved | Low impact | 4 | 1 | High impact | 5 | The system runs. However, some non-critical functionalities are not working.
3 | Students' eDollar balance is not in 2dp - it contains floating number | UI - Global Navbar.jsp | 2016-11-03 | 16:00 | Iris & Rachel | 2016-11-07 | 10:45 | Marc | Resolved | Low impact | 4 | 1 | Low impact | 1 | Unimportant. Typo error or small user interface alignment issues.
4 | Student was able to bid for a course where the exam falls on the same day and time | BidPlacement.java | 2016-11-03 | 16:00 | Iris & Rachel | 2016-11-07 | 10:56 | Marc | Resolved | High impact | 4 | 5
5 | Minimum bid price drops when a student drops their bid in round 2 | GetLiveBiddingTableServlet.jsva | 2016-11-03 | 16:00 | Iris & Rachel | 2016-11-07 | 15:13 | Ming Yi | Resolved | High impact | 4 | 5 | Bug Status
6 | Students' eDollar balance was not refunded after dropping a bid | StudentDropBidServlet.java | 2016-11-03 | 16:00 | Iris & Rachel | 2016-11-07 | 11:13 | Marc | Resolved | High impact | 4 | 5 | Resolved
7 | Users were unable to see their live bid results after bidding in round 2 | UI - bidSection.jsp | 2016-11-03 | 16:00 | Iris & Rachel | 2016-11-07 | 13:03 | Ming Yi | Resolved | Low impact | 4 | 1 | Unresolved
8 | Student has already dropped the section but the bid was still shown in drop bid page | StudentDropSectionServlet.java | 2016-11-03 | 16:00 | Iris & Rachel | 2016-11-07 | 11:32 | Marc | Resolved | High impact | 4 | 5
9 | "Course completed" error message was not shown when the course is already completed | BootstrapValidator.java | 2016-11-03 | 16:00 | Iris & Rachel | 2016-11-07 | 15:32 | Ming Yi | Resolved | High impact | 4 | 5
10 | "Invalid start" and "invalid end" was both shown when only "invalid start" should be shown | BootstrapValidator.java | 2016-11-03 | 16:00 | Iris & Rachel | 2016-11-07 | 11:52 | Marc | Resolved | High impact | 4 | 5
11 | Error message output is "invalid username/token" instead of "invalid token" | AuthenticationService.java | 2016-11-07 | 15:40 | Jackson | 2016-11-07 | 15:52 | Ming Yi | Resolved | High impact | 0 | 5
12 | Unable to update bid when update bid can be done as long as it is the same course | BootstrapService.java | 2016-11-07 | 15:55 | Jackson | 2016-11-07 | 16:32 | Ming Yi | Resolved | High impact | 0 | 5
13 | Student.csv info is not displayed | BootstrapService.java | 2016-11-07 | 15:55 | Jackson | 2016-11-07 | 17:24 | Jackson | Resolved | High impact | 0 | 5
14 | Number of lines loaded is wrong | BootstrapService.java | 2016-11-07 | 15:55 | Jackson | 2016-11-07 | 18:00 | Jackson | Resolved | High impact | 0 | 5
15 | ParseStartTime method does not take into account if there are letters contained in the string | BootstrapService.java | 2016-11-07 | 15:55 | Jackson | 2016-11-08 | 16:30 | Nilofar | Resolved | High impact | 1 | 5
16 | Student e-dollars is wrong | DumpUserService.java | 2016-11-07 | 18:03 | Jackson | 2016-11-08 | 19:14 | Nilofar | Resolved | High impact | 1 | 5
17 | Student were unable to get successful bids when vacancy > number of bids | Clearing round 1 - biddingRoundServlet.java | 2016-11-07 | 18:03 | Jackson | 2016-11-08 | 20:03 | Nilofar | Resolved | High impact | 1 | 5
18 | Section should be able to change when bid is updated | UpdateBidService.java | 2016-11-07 | 18:03 | Jackson | 2016-11-08 | 20:44 | Ming Yi | Resolved | High impact | 1 | 5
19 | "bid too low" error messsage when the bid should be bidded successfully | UpdateBidService.java | 2016-11-07 | 18:03 | Jackson | 2016-11-11 | 15:14 | Marc | Resolved | High impact | 4 | 5
20 | Info displayed is doubled | DumpSectionService.java | 2016-11-10 | 12:00 | Marc | 2016-11-11 | 15:53 | Marc | Resolved | High impact | 1 | 5
21 | Wrong display format for start time and end time - should be 800 instead of 8:00 | DumpTableService.java | 2016-11-10 | 12:00 | Marc | 2016-11-11 | 16:18 | Marc | Resolved | High impact | 1 | 5
22 | Display order for csv files are wrong | DumpTableService.java | 2016-11-10 | 12:00 | Marc | 2016-11-11 | 16:32 | Marc | Resolved | High impact | 1 | 5
23 | Display order for bid.csv is wrong | DumpTableService.java | 2016-11-10 | 12:00 | Marc | 2016-11-11 | 16:55 | Marc | Resolved | High impact | 1 | 5
24 | Bid was deleted but eDollars were not refunded | DeleteBidService.java | 2016-11-10 | 12:00 | Marc | 2016-11-11 | 17:42 | Nilofar | Resolved | High impact | 1 | 5
25 | Bids were displayed regardless of whether it is th most recently concluded round or not | BidDumpService.java | 2016-11-10 | 12:00 | Marc | 2016-11-11 | 18:34 | Nilofar | Resolved | High impact | 1 | 5
26 | Message was supposed to be "students" instead of "student" | BidStatusService.java | 2016-11-12 | 19:23 | Nilofar | 2016-11-12 | 20:03 | Marc | Resolved | High impact | 0 | 5
27 | MinBidValue for the bid was incorrect for all rounds | BidStatusService.java | 2016-11-12 | 19:23 | Nilofar | 2016-11-12 | 20:32 | Nilofar | Resolved | High impact | 0 | 5
28 | Message displayed was in wrong order | BidStatusService.java | 2016-11-12 | 19:23 | Nilofar | 2016-11-12 | 20:45 | Nilofar | Resolved | High impact | 0 | 5
29 | Bids displayed for round 2 start is wrong | BidStatusService.java | 2016-11-12 | 19:23 | Nilofar | 2016-11-12 | 21:14 | Nilofar | Resolved | High impact | 0 | 5
30 | Bids displayed for round 2 end is wrong | BidStatusService.java | 2016-11-12 | 19:23 | Nilofar | 2016-11-12 | 21:32 | Marc | Resolved | High impact | 0 | 5
[11 empty] | Total: | 134
Formulas:
Bug Lifetime(Days) = IF([Date Identified]="","",IF([Date Resolved]="",TODAY()-[Date Identified],[Date Resolved]-[Date Identified]))