## PP Metric
NOTE: Iteration 1 in Pplog was invalid. Therefore, iterations reflected in this schedule metric will start from Iteration 2.

## Iteration 2
ITERATION 2 | Planned | Actual
| PP Metric |  | (This corresponds to our actual Iteration 1)
Create login feature using the JWTUtility Jar file. Additionally, learn about session management through JSP and implement it into the BIOS. Test the login feature implemented and finally, complete the documentation for the parts that have been programmed. | 3.25 | 3.43
0.94752
Finish up the bootstrapping of data that do not possess proper validation and subsequently, write up the SQL code needed for the CRUD of data. Eventually, write up the web services that are needed to provide the JSON data. | 3 | 3.55
0.84507
Documenting login functionality especially Student and StudentDAO | 1 | 1.15
0.86957
Finish up bootstrapping validation and to finish up documentation of the bootstrapping functionality. | 4 | 7.03
0.56899
Improve the functionality of our login function, based on new knowledge acquired in class, by implementing an unauthorizedAccessPage and including it in all pages to protect them from users trying to log in through URL. Additionally, implement a session timeout function and draft a 404 error page for users who type an unavailable url. | 2 | 2.25
0.88889

## Iteration 3
ITERATION 3 | Planned | Actual
| PP Metric |  | (This corresponds to our actual Iteration 2)
Building UI For Bidding of section | 2 | 2.03
0.98522
Integrate with "Bootstrapping" and "Login" | 1.5 | 0.67
2.2388
Test and document of bidding of section functionality (Student) | 1.5 | 1.63
0.92025
Building Server-Side Logic of Bidding of section (Student) | 4.5 | 4.4
1.0227
Building Server-Side Logic of Bidding of section (Admin) | 4 | 4.13
0.96852
Test and document of bidding of section functionality (Admin) | 0.5 | 1.55
0.32258

## Iteration 4
ITERATION 4 | Planned | Actual
| PP Metric |  | (This corresponds to our actual Iteration 3)
1. Restructure GIT directory as specified in wiki; 2. integrating admin and student | 1 | 1.12
0.89286
Building server-side logic of viewing of bid (Admin) | 4 | 3.97
1.0076
Building UI for viewing of Bid (Admin) | 1.5 | 1.48
1.0135
Test and Debugging of Viewing of bid functionality (Admin) | 1 | 1.13
0.88496
Documentation of viewing of bid functionality (Admin) | 1 | 1.07
0.93458
Building Server-Side Logic of Dropping of bid (Student) | 4.5 | 4.1
1.0976
Building UI for dropping of Bid (Student) | 1.5 | 1.35
1.1111
Documentation of dropping of bid functionality (Student) | 1 | 0.87
1.1494
Integrate with bidding for section, bootstrapping, login | 2 | 2.02
0.9901
Test and Debugging of dropping of bid functionality (Student) | 1 | 0.93
1.0753

## Iteration 5
ITERATION 5 | Planned | Actual
| PP Metric |  | (This corresponds to our actual Iteration 4)
Building server-side logic of Clearing round 1(Admin) - charge students only when their bid is successful, set min bid price to $10 | 1.5 | 1.63
0.92025
Building server-side logic of Clearing round 1(Admin) - sort bid, derive minimum clearing price and drop bid if >1 bid is at minimum clearing price | 2 | 2.43
0.82305
Build UI for Clearing Round (Admin) | 2 | 2.02
0.9901
Building server-side logic for Clearing round 2(Admin) - include total available seats, total number of bids, min bid value | 1 | 1.07
0.93458
Building server-side logic for Clearing round 2(Admin) - set clearing price and recompute min bid value(make it real time) | 2.5 | 2.8
0.89286
Testing and debugging of Clearing Round 1 functionality (Admin) | 2 | 2.02
0.9901
Building server-side logic for Clearing round 2(Admin) - replenish e$ at end of bidding round for unsuccessful bids and confirm successful bids | 1 | 0.98
1.0204
Documentation Clearing Round 1 functionality (Admin) | 0.5 | 0.47
1.0638
Debugging after regression testing | 2.5 | 2.57
0.97276
Testing and debugging of Clearing Round 2 functionality (Admin) | 2 | 2.1 |  | x
0.95238
Documentation of Clearing Round 2 functionality (Admin) | 0.5 | 0.65
0.76923
Integration of Dropping of bid, Bidding for section, Bootstrapping and Login | 1 | 1
1
Debugging after regression testing | 2.5 | 1.83
1.3661
Testing and fixing any issues on AWS after deployment | 2 | 2.22
0.9009
Changing codes based on functional requirement changes as of 11 Oct | 1 | 1.12
0.89286

## Iteration 6
ITERATION 5 | Planned | Actual
| PP Metric |  | (This corresponds to our actual Iteration 5)
Building UI For "Dropping of Section" | 2 | 1.97
1.0152
Building Server-Side Logic of dropping of section - check "active" round, check "successful" bid, allow drop section, refund e$ | 2 | 2.05
0.97561
Building Server-Side Logic of dropping of section - rebid for section | 2 | 1.9
1.0526
Debugging for bootstrap validator | 1 | 0.92
1.087
Develop Web services for Authenticate | 1 | 1.37
0.72993
Develop Web services for Delete Bid | 2 | 2.13
0.93897
Develop Web services for Bootstrap | 2 | 3.92
0.5102
Develop Web services for Dump Table | 2 | 2.27
0.88106
Develop Web services for Start Round | 2 | 1.92
1.0417
Develop Web services for Stop Round | 1.5 | 1.57
0.95541
Develop Web services for Update Bid | 1.5 | 1.48
1.0135
Integration of all functions | 1 | 1.05
0.95238
Timetable functionality | 3 | 3.1
0.96774
Develop Web services for Drop Section | 2 | 2.28
0.87719
Develop Web services for Dump User | 2 | 1.73
1.1561
Debugging "Dropping of section" functionality | 2 | 1.85
1.0811
Documenting "Dropping of section" functionality | 2 | 1.82
1.0989
Documenting Web Services #1 | 2 | 2.17
0.92166
Develop Web services for Dump Bid | 1.5 | 1.82
0.82418
Develop Web services for Dump Section | 2 | 1.78
1.1236
Debugging for Web Services #2 | 3 | 3.28
0.91463
Documenting Web Services #2 | 1 | 1.1
0.90909
Debugging for Regression Testing #1 | 3 | 2.7
1.1111
Debugging for Web Services #1 | 3 | 3.03
0.9901
Debugging after Regression Testing #2 pt 1 | 2 | 2.05
0.97561
Debugging after Regression Testing #2 pt 2 | 2 | 2.6
0.76923
Debugging after Regression Testing #2 pt 3 | 2 | 2.33
0.85837
Debugging after Regression Testing #2 pt 4 | 4 | 3.1
1.2903

## Iteration 7
ITERATION 5 | Planned | Actual
PP Metric
Testing and debugging after UAT (Part I) | 3 | 3 | (This corresponds to our actual Iteration 6)
1
Testing and debugging after UAT (Part II) | 6 | 5.55
1.0811
Testing and debugging after UAT (Part III) | 4 | 2.92
1.3699
Ensure documentation of all code (Part I) | 4.5 | 4.95
0.90909
Performance optimizations to server | 4 | 4.08
0.98039
Ensure documentation of all code (Part II) | 6 | 5.83
1.0292
Implementating new web service, testing and debugging of new web service | 2 | -
#VALUE!
Testing and debugging after UAT(Part IV) | 4 | 4.45
0.89888
Regression testing and debugging | 2 | 2.05
0.97561