## Slide 1: In Class Demo
SEvivor

## Slide 2: Milestones
Supervisor Meeting
19 Sep 2016
PM Review
29 Sep 2016
In Class Demo
19 Sep 2016
Supervisor Meeting
24 Oct 2016
UAT
3 Nov 2016
Final Presentation
17 Nov 2016

## Slide 3: What We have Learnt
Allocated more time for regression testing
Gained a better understanding of the PM’s role (Diagrams, Metrics, Test Cases)
Gained a better understanding of schedule metrics (Days instead of hours)
Broke down tasks into smaller tasks for better estimation
Removed some unnecessary files
Uneven difficulty of Tasks mitigated (Yujian coached all of us on the more difficult tasks)

## Slide 4: Example of Breaking Down of Tasks
Breaking down of tasks
Building server-side logic for Clearing round 2(Admin) - include total available seats, total number of bids, min bid value
Building server-side logic for clearing round 2(Admin) – set clearing price and recompute min bid value.
Building server-side logic for clearing round 2(Admin) – replenish e$ at the end of bidding round for unsuccessful bids and confirm successful bids.

## Slide 5: Progress Since PM Review
Clear Round 1 & Clear Round 2
Code integration with previous functions
Deployment on Amazon Web Services
Testing and fixing of problems derived from AWS deployment
Iteration 4 : Clearing Round 1 & 2 | 
1 | Develop Sequence and Class Diagram for Iteration 4
2 | Building UI For "Clearing Round"
3 | Building Server-Side Logic of clearing round 1¦ clearing round 2 (Admin)
4 | Integrate with "Dropping of bid", "Bidding for section", "Bootstrapping" and "Login"
5 | Test "Clearing Round 1 ¦ Clearing Round 2" functionality
6 | Uploading to our AWS server
7 | Documenting "Clearing Round 1 ¦ Clearing Round 2" functionality

## Slide 6: Bug Metrics
Chart: Bug Metrics
| Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4
Low | 0 | 1 | 0 | 0
High | 1 | 3 | 4 | 9
Critical | 0 | 0 | 1 | 1
Iteration 1: 5
Iteration 2: 16
Iteration 3: 30
Iteration 4: 55

## Slide 7: Bug Log
10 Bugs were detected
All resolved within the day or the next day
No impact on Schedule metrics

## Slide 8: Schedule Metrics
Schedule Metrics |  |  |  | 
Iteration 1 | 18 |  | 18.5 | Re-estimated the tasks for the future iterations. Allocate more time to tasks in the upcoming iterations.
 | 0.97 |  |  | 
Iteration 2 | 6 | 6 |  | Our estimates were fairly accurate. Break down task a little bit more to get a better gauge of task timings.
 | 1.00 |  |  | 
Iteration 3 | 7 |  | 7 | Our estimates were fairly accurate. Break down task a little bit more to get a better gauge of task timings.
 | 1.00 |  |  | 
Iteration 4 | 13 |  | 13 | Our estimates were fairly accurate. Break down task a little bit more to get a better gauge of task timings.
 | 1.00 |  |  | 

## Slide 9: Plan for the next iteration
Ming Yi will be the next PM
  Drop Section
  JSON Web services
 | Iteration 5 : "Dropping of section“ “JSON Web services”
1 | Develop Sequence and Class Diagram for Iteration 5
2 | Building UI For "Dropping of Section"
3 | Building Server-Side Logic of dropping of section
4 | Integrate with "Clearing Round", "Dropping of bid", "Bidding for section", "Bootstrapping" and "Login"
5 | Test "Dropping of section" functionality
6 | Develop Web Services
7 | Uploading to our AWS server
8 | Documenting "Dropping of section" functionality

## Slide 10: SE IS SO NOT FUN!