## Slide 1: SE - Week 7 PM Review
G7-T5
Kong Yu Jian
Jackson Kwa
Marc Xu
Teh Ming Yi
M Has Nilofar

## Slide 2
Functionalities
Schedule (Iterations with Critical Path)
Metrics (Schedule, Pair Programming, Bug)
Roles & Responsibilities
Rotation plan
CONTENT

## Slide 3: FUNCTIONALITY
ADDING
View of bids (from the Admin side)
Calender feature (in Student Homepage)
DROPPING
None

## Slide 4: MODEL AND FRAMEWORK
MVC model

## Slide 5: SCHEDULE
No of iterations : 6
Feature Boxing

## Slide 6: ITERATION
Each iteration follows a mini waterfall process:
  Design + Planning + Requirement
  Coding
  Integration
  Deployment
  Testing & Debugging
  Documentation

## Slide 7: Iteration 1 (Completed) 01/09/2016 - 18/09/2016 (18 days)
PM: Marc
Tasks:
  Understanding requirements and drafting technical documents
  Diagramming (Use case, Logical Diagram, Class Diagram, Sequence Diagram)
  Wireframing UI
  Login and bootstrapping functionality
Milestones accomplished:
  NIL
Buffer used and left:
  0 used – 5 left
Evaluation:
  All tasks were completed on time.

## Slide 8
Project Requirements
1 day
ER + Logical + Class + Sequence Diagram
2 days
Learn new technologies [HTML + CSS + JS + Bootstrap + JSP]
2 days
Critical Path For Iteration 1

## Slide 9
Creation of SQL schema
1 day
Basic UI skeleton in Twitter Bootstrap
1.5 days
UI Wireframing
1 day

## Slide 10
Login functionality UI
1.5 day
Login functionality testing and troubleshooting
1 day
Login functionality server-side logic
1 day
Bootstrapping functionality server-side logic
2 day
Bootstrapping functionality validation
3 day
Bootstrap functionality testing and troubleshooting
1.5 day

## Slide 11
Integration of Login and Bootstrap Functionality
2 day
Preparation for Supervisor meeting
0.5 day
Iteration review, uploading documents & updating critical path
0.5 day
18 days in total

## Slide 12: Iteration 2 (Completed) 19/09/2016 - 24/09/2016 (6 days)
PM: Jackson
Tasks:
  Implement Bid Section function (Student) (Yu jian, Nilofar)
  Implement Bid Section function (Admin) (Ming Yi, Marc)
Milestones accomplished:
  Supervisor Meeting (19 Sept)
Buffer used and left:
  1 day (to catch up on overdue work from the previous iteration)
  4 left
Evaluation:
  All tasks were completed on time.

## Slide 13
Bidding section functionality Server-side logic [Student]
1 day
Bidding section functionality testing and troubleshooting
1.5 day
Bidding Section functionality UI
1 day
Bidding section functionality Server-side logic [Admin]
2 day
Bidding section functionality testing and troubleshooting
1 day
Critical Path For Iteration 2

## Slide 14
Bidding section functionality integration
1 day
Prepare documents and presentation for PM Review
1 day
6 days in total

## Slide 15: Iteration 3 (in-progress) 26/09/2016 - 02/10/2016 (7 days)
PM: Nilofar
Tasks:
  Implement Dropping of Bid (Student) (Yu Jian, Marc)
  Implement Viewing / Dropping of Bids (Admin) (Ming Yi, Jackson)
Milestones accomplished:
  PM Review (29 Sept)
Buffer used and left:
  0 used – 4 left

## Slide 16
View/Drop bid UI [Admin]
1.5 day
View/Drop bid functionality testing and troubleshooting
1 day
View/Drop bid Server-side logic [Admin]
1.5 day
Dropping bid UI [Student]
1 day
Dropping bid Server-side logic [Student]
1 day
Dropping bid functionality testing and troubleshooting
1 day
Critical Path For Iteration 3

## Slide 17
Drop bid functionality integration
1 day
Functionality testing with test cases & deployment
2 day
7 days in total

## Slide 18: Iteration 4 (pending) 03/10/2016 - 15/10/2016 (13 days)
PM: Marc
Tasks:
  Implement Clearing Round 1 (Nilofar, Jackson)
  Implement Clearing Round 2 (Ming Yi, Yu Jian)
Milestones to accomplish:
  In-class demo (13 Oct)

## Slide 19
Clearing round UI
3 day
Clearing round 1 functionality testing and troubleshooting
3 day
Clearing round Server-side logic [round 1]
3 day
Clearing round Server-side logic [round 2]
3 day
Clearing round 2 functionality testing and troubleshooting
2 day
Critical Path For Iteration 4

## Slide 20
Clearing round functionality integration
2 day
Functionality testing with test cases & deployment
2 day
13 days in total

## Slide 21: Iteration 5 (pending) 16/10/2016 - 04/11/2016 (20 days)
PM: Ming Yi
Tasks:
  Implement Drop Section function (Student) (Marc, Jackson)
  Develop Web Services (Yu Jian, Nilofar)
  Final Deployment (Yu Jian, Nilofar)
Milestones to accomplish:
  Supervisor Meeting (24 Oct)
  UAT (in-class) (3 Nov)

## Slide 22
Dropping section UI
3 day
Dropping section functionality testing and troubleshooting
3 day
Dropping section Server-side logic
3 day
Develop web services [Part 2]
4 day
Web services functionality testing and troubleshooting
4 day
Develop web services [Part 1]
4 day
Critical Path For Iteration 5

## Slide 23
Integration with all previous functionalities
3 day
AWS deployment & further test case analysis
5 day
20 days in total

## Slide 24: Iteration 6 (pending) 05/11/2016 - 18/11/2016 (14 days)
PM: Yu Jian
Tasks:
  Ensure documents are uploaded
  Cross-check project with requirements
  Final Deployment
  Final Presentation
Milestones to accomplish:
  Final Presentation (17 Nov)
  Project Submission (13 Nov)

## Slide 25
Ensure required documents & deliverables uploaded
4 day
Rehearsals
5 day
Preparation of materials for presentation
5 day
FINAL PRESENTATION + SUBMISSION
Critical Path For Iteration 6
14 days in total

## Slide 26: METRICS (Task, Pair Programming, Bug)

## Slide 27: SCHEDULE METRIC

## Slide 28: PAIR-PROGRAMMING METRIC (Iteration 1)

## Slide 29: PAIR-PROGRAMMING METRIC (Iteration 1)

## Slide 30: PAIR-PROGRAMMING METRIC (Iteration 2)

## Slide 31: BUG METRIC

## Slide 32: MILESTONE IC’S
PM | Managing Period | Milestone
Marc | 1st Sep – 18th Sep | -
Jackson | 19th Sep – 25th Sep | Supervisor Meeting 1
Nilofar | 26th Sep – 2nd Oct | PM Review
Marc | 3rd Oct – 15th Oct | Application In-class demo
Ming Yi | 16th Oct – 4th Nov | Supervisor Meeting 2, UAT
Yu Jian | 5th Nov – 18th Nov | Final Presentation

## Slide 33
Functionality | Yu Jian | Jackson | Marc | Ming Yi | Nilofar
Bootstrap | √ | √ |  |  | 
Login |  |  |  | √ | √
Bidding |  |  | √ |  | √
Clearing Round 1 |  | √ |  |  | √
Clearing Round 2 | √ |  |  | √ | 
Drop Bid |  | √ |  | √ | 
Drop Section | √ |  | √ |  | 
View Bidding Results | √ |  |  | √ | 
ROLES & RESPONSIBILITIES

## Slide 34: Pair Programming Teams
Iteration | PM | PP1 | PP2
1 | Marc | Ming Yi, Nilofar | Jackson, Yu jian
2 | Jackson | Ming Yi, Marc | Yu Jian, Nilofar
3 | Nilofar | Marc, Yu Jian | Ming Yi, Jackson
4 | Marc | Nilofar, Jackson | Ming Yi, Yu Jian
5 | Ming Yi | Nilofar, Yu Jian | Jackson, Marc
6 | Yu Jian | Nilofar, Marc | Ming Yi, Jackson

## Slide 35: Rotation plan

## Slide 36: Thank you