## ClearRound1
Number | Description | Test Inputs (depending on which user we use to test?) | Test Procedure | Expected Results | Actual Results | Status (Pass/Fail)
2016-10-07
Clear Round 1 | [5 empty] | Functional Test
1 | Check if bid below $10 would be able to go through | 1) user: "jerry.ng.2009", Course-Section:"IS100-S1", bidAmount="9" | During active Round 1, try to input a bid with bidAmount <e$10 | Bid will be unable to be added to successful bid list | Bid will be unable to be added to successful bid list | Pass
2 | Check what happens if there are no bid placed for this particular section of the course | 1) user: "admin" Course-Section:"ECON001-S1" | Stop Round 1, check admin homepage for bids for a particular section | "No Bids for this Course-Section" | "No Bids for this Course-Section" | Pass
3 | Check that the clearing price is derived from the amount of vacancies in that particular Course and Section | 1) user: "admin", Course-section:"IS100-S1" | Stop Round , check admin homepage for bids for the particular section | Clearing price="12" | Clearing price="12" | Pass
3a | Check if only one bid at clearing price will be able to go through | 1) user: "admin", Course-section:"IS100-S1" | Continue from part 3 | calvin:"successful", ben: "unsuccessful" | calvin:"successful", ben: "unsuccessful" | Pass
4 | Check if more than one bid at clearing price will be able to go through | 1)user:"jerry.ng.2009", Course-section:"IS100-S1",bidAmount="12" 2) user: "admin",course-section: "IS100-S1" | Place bid accordingly. Stop Round , check admin homepage for bids for the particular section | jerry's and calvin's bids will be dropped. Clearing price="12" | jerry's and calvin's bids will be dropped. Clearing price="12" | Pass
4a | Validate if bids were sorted from high to low | 1) user: "admin", Course-section:"IS100-S1" | Continue from part 4 | Bids will be displayed with status, clearing price="12" | Bids will be displayed with status, clearing price="12" | Pass
4b | Check if unsuccessful bids will be refunded | 1) user:"jerry.ng.2009" 2)userid:"calvin.ng.2009" 3)userid:"ben.ng.2009" | Continue from part 4a, check user's account for refunded e$ | 1) user:"jerry.ng.2009", e$:"200" 2)userid:"calvin.ng.2009", e$:"200" 3)userid:"ben.ng.2009", e$:"200" | 1) user:"jerry.ng.2009", e$:"200" 2)userid:"calvin.ng.2009", e$:"200" 3)userid:"ben.ng.2009", e$:"200" | Pass
4c | Check that successful bids by the Students will be deducted in accordance with the exact amount bidded | 1) userid:"maggie.ng.2009" 2)userid:"nielson.ng.2009" 3)userid:"olivia.ng.2009" | Continue from part 4b, check user's account for deducted e$ | 1) userid:"maggie.ng.2009", e$="180" 2)userid:"nielson.ng.2009", e$:"179" 3)userid:"olivia.ng.2009", e$:"178" | 1) userid:"maggie.ng.2009", e$="180" 2)userid:"nielson.ng.2009", e$:"179" 3)userid:"olivia.ng.2009", e$:"178" | Pass
5 | Check if bids for a section which has vacancy more than the number of bids, are successful | 1) userid:"amy.ng.2009", course-section:"IS101-S1" bidAmount:"12" 2) userid:"gary.ng.2009", course-section:"IS101-S1" bidAmount:"12" | Place bid accordingly. Stop Round , check admin homepage for bids for the particular section | min bid price = "10" | min bid price = "10" | Pass
6 | When section size = 1 | biding amount S1 = S2. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:0 Failure: 2" | Displays bidding results "Course: S100 Section: S1 Success:0 Failure: 2" | Pass
7 | When section size = 1 | biding amount S1 != S2. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:1 Failure: 1" | Displays bidding results "Course: S100 Section: S1 Success:1 Failure: 1" | Pass
8 | When section size = 2 | biding amount S1 != S2 !=S3 | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:2 Failure: 1" | Displays bidding results "Course: S100 Section: S1 Success:2 Failure: 1" | Pass
9 | When section size = 2 | biding amount S1 != S2 = S3. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:1 Failure: 2" | Displays bidding results "Course: S100 Section: S1 Success:1 Failure: 2" | Pass
10 | When section size = 2 | biding amount S1 = S2 != S3. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:0 Failure: 3" | Displays bidding results "Course: S100 Section: S1 Success:0 Failure: 3" | Pass
11 | When section size = 2 | biding amount S1 = S2 = S3. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:0 Failure: 3" | Displays bidding results "Course: S100 Section: S1 Success:0 Failure: 3" | Pass
12 | When section size = 3 | biding amount S1 != S2 != S3 != S4. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:3 Failure: 1" | Displays bidding results "Course: S100 Section: S1 Success:3 Failure: 1" | Pass
13 | When section size = 3 | biding amount S1 != S2 != S3 = S4. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:2 Failure: 2" | Displays bidding results "Course: S100 Section: S1 Success:2 Failure: 2" | Pass
14 | When section size = 3 | biding amount S1 != S2 = S3 = S4. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:1 Failure: 3" | Displays bidding results "Course: S100 Section: S1 Success:1 Failure: 3" | Pass
15 | When section size = 3 | biding amount S1 != S2 = S3 != S4. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:1 Failure: 3" | Displays bidding results "Course: S100 Section: S1 Success:1 Failure: 3" | Pass
16 | When section size = 3 | biding amount S1 = S2 != S3 != S4. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:3 Failure: 1" | Displays bidding results "Course: S100 Section: S1 Success:3 Failure: 1" | Pass
17 | When section size = 3 | biding amount S1 = S2 = S3 != S4. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:1 Failure: 3" | Displays bidding results "Course: S100 Section: S1 Success:1 Failure: 3" | Pass
18 | When section size =3 | biding amount S1= S2 = S3 = S4. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:0 Failure: 4" | Displays bidding results "Course: S100 Section: S1 Success:0 Failure: 4" | Pass
19 | When section size = 10 | biding amount S1!= S2 != S3 != S4 != S5 !=S6 != S7=S8= S9= S10 = S11. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:6 Failure: 5" | Displays bidding results "Course: S100 Section: S1 Success:6 Failure: 5" | Pass
20 | When section size = 10 | biding amount S1!= S2 != S3 != S4 != S5 !=S6 = S7=S8= S9= S10 = S11. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:5 Failure: 6" | Displays bidding results "Course: S100 Section: S1 Success:5 Failure: 6" | Pass
21 | When section size = 10 | biding amount S1!= S2 != S3 != S4 != S5 =S6 = S7=S8= S9= S10 = S11. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:4 Failure: 7" | Displays bidding results "Course: S100 Section: S1 Success:4 Failure: 7" | Pass
22 | When section size = 10 | biding amount S1!= S2 != S3 != S4 = S5 =S6 = S7=S8= S9= S10 = S11. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:3 Failure: 9" | Displays bidding results "Course: S100 Section: S1 Success:3 Failure: 9" | Pass
23 | When section size = 10 | biding amount S1!= S2 = S3 = S4 = S5 =S6 = S7=S8= S9= S10 = S11. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:1 Failure: 10" | Displays bidding results "Course: S100 Section: S1 Success:1 Failure: 10" | Pass
24 | When section size = 10 | biding amount S1= S2 = S3 = S4 = S5 =S6 = S7=S8= S9= S10 = S11. | 1) Log in as Admin 2) BootStrap File 3) Login as various students 4) Place the different bids where number of bids > vacancies, with one bid being the lowest amount 5) Log in as Admin 6) End Round 1 7) Check Admin Homepage | Displays bidding results "Course: S100 Section: S1 Success:0 Failure: 11" | Displays bidding results "Course: S100 Section: S1 Success:0 Failure: 11" | Pass